## Slide 1: 3. Project Organization and Management

## Slide 2: Outline
An Overview of Project Management
Project Management Activities
Software Life Cycle Model

## Slide 3: 1. An Overview of Project Management

## Slide 4: 1.1 History of Project Management
Some people argue that building the Egyptian pyramids was a project, as was building the Great Wall of China
Most people consider the Manhattan Project to be the first project to use “modern” project management
  This three-year, $2 billion (in 1946 dollars) project had a separate project manager and a technical manager
Notes: Money is less valuable than before

## Slide 5: 1.2 The Triple Constraint of Project Management
Every project is constrained in different ways by its:
  Scope:
    What work will be done as part of the project?
    What unique product, service, or result does the customer or sponsor expect from the project?
    How will the scope be verified?
  Time:
    How long should it take to complete the project?
    What is the project’s schedule?
    How will the team track actual schedule performance?
    Who can approve changes to the schedule?

## Slide 6
Every project is constrained in different ways by its:
  Cost:
    What should it cost to complete the project?
    What is the project’s budget?
    How will costs be tracked?
    Who can authorize changes to the budget?
It is the project manager’s duty to balance these three often competing goals.

## Slide 7
Successful project management means meeting all three goals (scope, time, and cost) – and satisfying the project’s sponsor!

## Slide 8: 1.3 Project Management Framework

## Slide 9: 1.4 Tasks and Work Products
A task is a well-defined work assignment for a role
A work product is a tangible item that results from a task
  An object model
  A class diagram
  A piece of source code
  A document
  …

## Slide 10
Task
*
Work
Activity
Project Function
«invariant»
duration = project.duration

## Slide 11: Work Products, Work Packages, and Roles
Work Package: A description of the work products to be produced, the resource needed, duration (expected), work produces and dependencies
produced-by
*
Task
*
Work
Activity
Project Function
Project Deliverable
Internal Work Product
Work Product
Set of Work Products
Outcome
*
Work Package
describes
Notes: We assign them to participants to do the work.
An example of a small work package is an action item, which contains only the name of the participant, the description of the task, the time needed.
Any work product to be delivered to the customer is called a deliverable

## Slide 12: Example: Let‘s Build a House
What are the activities that are needed to build a house?

## Slide 13: What is the problem?
Your boss: “How long will this take?”
You: “Between 1 and 6 months.”
People are not happy when you respond that way.
  You figure out that finishing anytime before six months will meet your promise.
  Your boss figures that with some hard work you can be done in a month!
In reality, you don’t have the slightest clue how long it will take, because you don’t know the work to be done.
Solution: Use divide and conquer
  To give a good answer you have to break the work down into activities for which you can get good timing estimates
  From these estimates you compute the estimated project duration

## Slide 14: Activities to obtain good time estimates
Identify the work that needs to be done
  Work breakdown structure (WBS)
Identify the dependency between work units
  Dependency Graph
Estimate the duration of the work to be done
  Schedule

## Slide 15: Typical activities when building a house
Surveying
Excavation
Request Permits
Buy Material
Lay foundation
Build Outside Wall
Install Exterior Plumbing
Install Exterior Electrical
Install Interior Plumbing
Install Interior Electrical
Install Wallboard
Paint Interior
Install Interior Doors
Install Floor
Install Roof
Install Exterior Doors
Paint Exterior
Install Exterior Siding
Buy Pizza
Finding these activities is a brainstorming activity.
It requires similar activities used during analysis (use case modeling)

## Slide 16: Hierarchical organization of the activities
Building the house consists of
  Prepare the building site
  Building the Exterior
  Building the Interior
Preparing the building site consists of
  Surveying
  Excavation
  Buying of material
  Laying of the foundation
  Requesting permits

## Slide 17: Partial Work Breakdown Structure
Notes: [ˈplʌmɪŋ]
Sewer pipes 下水道

## Slide 18: From the WBS to the Dependency Graph
The work breakdown structure does not show any temporal dependence among the activities/tasks
  Can we excavate before getting the permit?
  How much time does the whole project need if I know the individual times?
    What can be done in parallel?
  Are there any critical actitivites, that can slow down the project significantly?
Temporal dependencies are shown in the dependency graph
  Nodes are activities
  Lines represent temporal dependencies

## Slide 19: Building a House (Dependency Graph)
START
Request
Survey
ing
Excava
tion
Buy
Material
Founda
tion
Build
Outside
Wall
Install
Exterior
Plumbing
Install
Interior
Plumbing
Install
Exterior
Electrical
Install
Interior
Electrical
Install
Exterior
Siding
Install
Wallboard
Paint
Exterior
Install
Roofing
Install
Flooring
Paint
Interior
Install
Interior
Doors
Install
Exterior
Doors
FINISH
The activity
„Buy Material“ must
Precede the activity
„Lay foundation“
Lay

## Slide 20: Building a House (PERT Chart)
Duration
Start Time
Slack Time
Each Activity has a start time and an estimated duration
START
8/27/94
0
0
Request
Permits
8/27/94
15
0
Survey
ing
8/27/94
3
12
Excava
tion
9/17/94
10
0
Legend
8/29/94
0
Buy
Material
10/1/94
10
0
Lay
Founda
tion
10/15/94
15
0
Build
Outside
Wall
11/5/94
20
0
Install
Exterior
Plumbing
12/3/94
10
12
Install
Interior
Plumbing
12/3/94
12
0
Install
Exterior
Electrical
12/17/94
10
12
Install
Interior
Electrical
12/21/94
15
0
Install
Exterior
Siding
12/31/94
8
12
Install
Wallboard
1/11/95
9
0
Paint
Exterior
1/12/95
5
12
Install
Roofing
1/19/95
9
12
Install
Flooring
1/22/95
18
0
Paint
Interior
1/22/95
11
0
Install
Interior
Doors
2/8/95
7
0
Install
Exterior
Doors
1/19/95
6
15
FINISH
2/16/95
0
0
0

## Slide 22: Model of a Project from a project manager’s point of view.
*
Resource
Participant
Fund
Equipment
Schedule
Task
*
Activity
con-
Facility
*
Staff
Department
Team
produces
Work
Set of Work
*
Product
Products
*
Internal
Project
Work
respon-
sumes
Package
Role
*
des-
*
cribes
Deliverable
sible
plays
for
Organi-
zation
Structure
*
*
depends
Work Product
Project Function
Project
Outcome
Work
Organizational
Unit
Work
Breakdown

## Slide 23: 1.5 Project Agreement, Problem Statement vs SPMP

## Slide 24: Project Agreement
Document written for a client that defines:
  the scope, duration, cost and deliverables for the project.
  the exact items, quantities, delivery dates, delivery location.
Client: Individual or organization that specifies the requirements and accepts the project deliverables.
Can be a contract, a statement of work, a business plan, or a project charter.
Deliverables (= Work Products that will be delivered to the client:
  Documents
  Demonstrations of function
  Demonstration of nonfunctional requirements
  Demonstrations of subsystems

## Slide 25: 2. Project Management Activities

## Slide 26: 2.1 Four Management Activities
Planning the Project
Organizing the Project
Controlling the Project
Terminating the Project

## Slide 27: 2.2 Planning the Project
Problem Statement
Top-level Design
Organization
Task Model
Schedule
Requirements Analysis
Document (RAD)
System Design
Document (SDD)
Software Project
Management Plan (SPMP)
Project Agreement
Project Planning Products
Deliverables
Notes: Problem statement: a short document describing the problem the system should address, the target environment, client deliverables, and acceptance criteria
Top-level design: it represents the initial decomposition of the system into subsystems
SPMP: all the managerial aspects of the project

## Slide 28: 2.3 Organizing the Project
Setting up the communication infrastructure
  Schedule Modes
  Event-based modes
Identifying skills
  Application domain skills
  Communication skills
  Technical skills
  Quality skills
  Management skills

## Slide 29
Assigning management roles
Assigning technical roles
Dealing with skill shortages
Selecting team sizes
Assembling the teams
Kick-off meeting
Agreeing on project scope

## Slide 30: 2.4 Controlling the Project
Decision making relying on collecting accurate status information
  Meetings
  Sharp milestones
  Project reviews
  Code inspections
  Prototype demonstration

## Slide 31
Metrics
  Financial status
  Technical progress
  Stability
  Modularity
  Maturity

## Slide 32: 2.5 Terminating the Project
Accepting the system
  The presentation of the system and the approval of the client according to acceptance criteria set forth in the Project Agreement
Installation
  It includes the field test of the system, the comparison of the system results with the legacy system, the rollout of the legacy system, and the training of users
Postmortem
  Each project provides a chance for learning

## Slide 33: 3. Software Life Cycle Model

## Slide 34
A software life cycle model represents all the activities and work products necessary to develop a software system

## Slide 35: The waterfall model of software development is an activity-centered view of the software life cycle.
Requirements
Process
System
Allocation
Process
Project
Initiation
Process
Concept
Exploration
Process
Design
Process
Implementation
Process
Installation
Process
Operation &
Support Process
Verification
& Validation
Process

## Slide 36: V-Model of software development.
System
Requirements
Analysis
Implementation
Preliminary
Design
Detailed
Design
Software
Requirements
Elicitation
Operation
Client
Acceptance
Requirements
Analysis
Unit
Test
System
Integration
& Test
Component
Integration
& Test

## Slide 37: Boehm’s spiral model (Adapted from [Boehm, 1987]).
Notes: This model of development combines the features of the prototyping model and the waterfall model. The spiral model is favored for large, expensive, and complicated projects.
The final system is constructed, based on the refined prototype

## Slide 38: Workflows in the unified software life cycle
*
releases
*
Design
Requirements
Implementation
Deployment
Unified Process
Software Life Cycle
Management
*
Environment
Assessment
Workflow
Artifact
Iteration
Transition
Construction
Inception
Elaboration
Phase
4
Cycle
*
Product
Unified Process Model

## Slide 39: States of a Software System called phases in the Unified Process.
Inception
Elaboration
Construction
Transition

## Slide 40: The seven workflows in the Unified Process.

## Slide 41: Capability Maturity Model (CMM)
CMM was developed at the Software Engineering Institute (SEI) at Carnegie-Melon University in Pittsburgh, PA, funded largely by the U.S. Defense Department.
CMM is design to measure, and thereby improve, the process of software development.
SEI establishes standards; it does not perform evaluations of individual firms.
Evaluations of firms are done by third parties; these third-party evaluators have varying degrees of expertise and creditability.
The highest level of CMM is Level Five; less than a hundred organizations in the world are certified as Level Five.
CMM is similar to ISO 9000 and 9001; but while CMM focuses primarily on improving performance, ISO 9000 and 9001 focus on establishing and maintaining careful documentation, procedures, and standards.

## Slide 42
What are the Five Levels of CMM?
Initial – poorly controlled; ad hoc; difficult to repeat successful activities; dependent upon the skills of the individual developers
Repeatable – disciplined processes; can repeat successful activities and tasks; developers learn from each other
Defined – standard, consistent processes; a database of development “best practices” is created and maintained; these “best practice” are readily available and understood
Managed – all development activities follow these corporate “best practices”; compliance with these development standards is mandatory
Optimizing – continuous process of seeking out best practices from around the world; active, continuous improvement

## Slide 43: Summary
Software development as a Project
Project Management is a modern approach to coordinate complex task teams
There are different Software Life Cycle Models with different characteristics.

## Slide 44: Thanks cao-jian@cs.sjtu.edu.cn
Some materials come from Bernd Bruegge’s PPT, others from Internet
csis.pace.e